## Project Plan
Project Development Plan and Gantt Chart
ML-Assisted Self-Healing of a Mining Distribution Feeder with Selective Fault Isolation
BEng Thesis - Victoire C. Chimundu
Project start |  | 2025-07-01 |  | Status date |  | 2026-08-10
Project finish |  | 2026-08-15 |  | Overall complete |  | 98.95%
Total duration (calendar days) |  | 411 |  | Tasks / milestones |  | 10 / 4
Chart data - do not edit
WBS | Task / milestone | Type | Pred. | Start | Finish | Days | % | Status | Evidence in thesis | Plot start | Plot days | Complete | Remaining | Chart label
1 | Conception and proposal | Phase | - | 2025-07-01 | 2026-02-15 | 230 | 100% | Complete | Chapter 1 | 2025-07-01 | 230 | 230 | 0 | 1 Conception and proposal
1.1 | Topic conception (after KCM site visit) | Task | - | 2025-07-01 | 2025-09-15 | 77 | 100% | Complete | Section 1.1 | 2025-07-01 | 77 | 77 | 0 | 1.1 Topic conception (after KCM site visit)
1.2 | FYP proposal development | Task | 1.1 | 2025-09-16 | 2025-12-15 | 91 | 100% | Complete | Sections 1.2-1.4 | 2025-09-16 | 91 | 91 | 0 | 1.2 FYP proposal development
M1 | Proposal submitted | Milestone | 1.2 | 2025-12-15 | 2025-12-15 | 1 | 100% | Complete | - | 2025-12-12 | 6 | 6 | 0 | M1 Proposal submitted
1.3 | Concept development and refinement | Task | 1.2 | 2025-10-25 | 2026-01-15 | 83 | 100% | Complete | Chapter 2; Section 2.5 | 2025-10-25 | 83 | 83 | 0 | 1.3 Concept development and refinement
1.4 | Scope simplification and title finalisation | Task | 1.3 | 2026-01-16 | 2026-02-15 | 31 | 100% | Complete | Section 1.5 | 2026-01-16 | 31 | 31 | 0 | 1.4 Scope simplification and title finalisation
M2 | Title and scope finalised | Milestone | 1.4 | 2026-02-15 | 2026-02-15 | 1 | 100% | Complete | - | 2026-02-12 | 6 | 6 | 0 | M2 Title and scope finalised
2 | Modelling, dataset and machine learning | Phase | 1 | 2026-03-01 | 2026-08-07 | 160 | 100% | Complete | Chapters 3-5 | 2026-03-01 | 160 | 160 | 0 | 2 Modelling, dataset and machine learning
2.1 | Feeder Simulink modelling | Task | 1.4 | 2026-03-01 | 2026-07-05 | 127 | 100% | Complete | Chapter 4; Sections 4.2-4.5 | 2026-03-01 | 127 | 127 | 0 | 2.1 Feeder Simulink modelling
2.2 | Topology rebuild and dataset generation | Task | 2.1 | 2026-06-05 | 2026-07-10 | 36 | 100% | Complete | Section 3.3; Table 3.3 | 2026-06-05 | 36 | 36 | 0 | 2.2 Topology rebuild and dataset generation
M3 | Labelled dataset complete | Milestone | 2.2 | 2026-07-10 | 2026-07-10 | 1 | 100% | Complete | - | 2026-07-07 | 6 | 6 | 0 | M3 Labelled dataset complete
2.3 | Machine learning and robustness analysis | Task | 2.2 | 2026-06-05 | 2026-07-12 | 38 | 100% | Complete | Sections 5.4, 5.7 | 2026-06-05 | 38 | 38 | 0 | 2.3 Machine learning and robustness analysis
2.4 | Autonomous FDIR implementation | Task | 2.3 | 2026-06-05 | 2026-08-07 | 64 | 100% | Complete | Sections 4.8, 5.8 | 2026-06-05 | 64 | 64 | 0 | 2.4 Autonomous FDIR implementation
3 | Writing and submission | Phase | - | 2026-05-01 | 2026-08-15 | 107 | 95.14% | In progress | Chapters 1-6 | 2026-05-01 | 107 | 102 | 5 | 3 Writing and submission
3.1 | Thesis drafting | Task | - | 2026-05-01 | 2026-08-08 | 100 | 100% | Complete | Chapters 1-6 | 2026-05-01 | 100 | 100 | 0 | 3.1 Thesis drafting
3.2 | Corrections, documentation and submission | Task | 3.1 | 2026-06-01 | 2026-08-15 | 76 | 90% | In progress | Appendices A-C | 2026-06-01 | 76 | 68 | 8 | 3.2 Corrections, documentation and submission
M4 | Thesis submission | Milestone | 3.2 | 2026-08-15 | 2026-08-15 | 1 | 0% | Not started | - | 2026-08-12 | 6 | 0 | 6 | M4 Thesis submission
How to use this sheet
- Blue cells (Start, Finish, %) are the only inputs - edit those and everything else, including the Gantt chart, updates automatically.
- Black cells are formulas. Phase rows roll up from their child tasks; Days = Finish - Start + 1; the % on a phase row is duration-weighted.
- Columns K-O drive the chart only. Milestones are stored with Start = Finish (zero duration) and are widened to a 6-day marker so they remain visible at this time scale.
- The chart plots three stacked series: Plot start (no fill, positions the bar), Complete and Remaining. Shading: phase rows black, tasks grey, milestones solid black markers, outstanding work light grey.
- Dates were reconstructed from the project record; adjust any that differ from your own log and the chart will follow.
Formulas:
Start = MIN([Start, row below]:E16)
Finish = MAX([Finish, row below]:F16)
Plot start = IF([Type]="Milestone",[Start]-3,[Start])